## ℹ Instructions
MAINTENANCE PLANNING TOOL — USER GUIDE
OVERVIEW
This workbook contains 5 sheets: Instructions, Annual Planner (Gantt), Work Order Register, Resource Allocation, and KPI Summary. All sheets link together automatically.
STEP 1 — Settings
Go to the 'Settings' tab. Enter your facility name, planning year, total planned hours per month, and the list of technicians. These feed into the Resource sheet.
STEP 2 — Annual Planner
Go to '📅 Annual Planner'. Add each maintenance task: enter the Task ID, description, equipment tag, type (PM/PdM/CBM/Overhaul), responsible person, planned start week, and duration in weeks. The Gantt bars fill automatically.
STEP 3 — Work Orders
Go to '📋 Work Orders'. Log each work order as it is raised: WO number, linked task, equipment, priority, status, estimated and actual hours, and cost. Status dropdown controls the row colour (Planned / In Progress / Complete / Overdue / Cancelled).
STEP 4 — Resource Allocation
Go to '👥 Resources'. This sheet shows planned hours per technician per month, compared to their available hours. Over-allocated months are highlighted in red automatically.
STEP 5 — KPI Summary
Go to '📊 KPIs'. All metrics (PM Compliance, Schedule Adherence, Backlog, Cost Variance) calculate automatically from the Work Order sheet. No manual entry needed.
COLOUR CODING
Yellow cells = manual input required. Blue cells = auto-calculated (do not edit). Green rows = Complete. Red rows = Overdue. Orange rows = In Progress. Gantt bars: dark fill = planned window, green fill = complete.
CONTACT
Template by Katleho Khoarane ¦ Mechanical Engineer ¦ MEng Candidate — CUT ¦ Turbomachinery · Mining · Energy ¦ linkedin.com/in/katleho-khoarane

## ⚙ Settings
SETTINGS — Edit yellow cells only
Facility Name | Acme Mining — Plant A
Planning Year | 2025
Total weeks in year | 52
Std hours/day | 8
Std working days/month | 22
TECHNICIANS (one per row below)
T. Mokoena
S. Dlamini
R. Botha
K. Sithole
J. van Wyk
A. Mahlangu
NAMED_TECH_START

## 📅 Annual Planner
ANNUAL MAINTENANCE PLANNER — GANTT VIEW
[9 empty] | JAN |  |  |  | FEB |  |  |  | MAR |  |  |  |  | APR |  |  |  | MAY |  |  |  | JUN |  |  |  | JUL |  |  |  |  | AUG |  |  |  | SEP |  |  |  | OCT |  |  |  |  | NOV |  |  |  | DEC
Task ID | Description | Equipment | Type | Responsible | Start Week | Duration (wks) | Status | Priority | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
T-001 | 30,000hr PM — Feed Pump P-101 | P-101 | PM | T. Mokoena | 1 | 1 | Planned | High | █
T-002 | Gearbox oil change — GB-001 | GB-001 | PM | S. Dlamini | 2 | 1 | Planned | Medium |  | █
T-003 | Conveyor belt inspection — CV-001 | CV-001 | Inspection | R. Botha | 3 | 1 | Planned | High |  |  | █
T-004 | Vibration analysis — M-101 | M-101 | PdM | K. Sithole | 4 | 1 | Planned | High |  |  |  | █
T-005 | Crusher overhaul | M-101 | Overhaul | T. Mokoena | 5 | 4 | Planned | Critical |  |  |  |  | █ | █ | █ | █
T-006 | Lubrication round — all pumps | P-101 | Lubrication | J. van Wyk | 1 | 1 | Planned | Low | █
T-007 | Ball mill liner replacement | M-102 | Overhaul | A. Mahlangu | 12 | 3 | Planned | Critical | [11 empty] | █ | █ | █
T-008 | Cooling fan bearing replacement | FN-001 | PM | R. Botha | 8 | 1 | Planned | Medium | [7 empty] | █
T-009 | Compressor valve overhaul | C-101 | Overhaul | S. Dlamini | 16 | 2 | Planned | High | [15 empty] | █ | █
T-010 | Tailings pump impeller check | P-102 | Inspection | K. Sithole | 20 | 1 | Planned | Medium | [19 empty] | █
T-011 | Conveyor CV-002 belt tension | CV-002 | PM | J. van Wyk | 24 | 1 | Planned | Low | [23 empty] | █
T-012 | Gearbox GB-002 oil analysis | GB-002 | PdM | T. Mokoena | 26 | 1 | Planned | Medium | [25 empty] | █
T-013 | Motor alignment check — M-101 | M-101 | Inspection | A. Mahlangu | 30 | 1 | Planned | High | [29 empty] | █
T-014 | Annual safety valve test | C-101 | Inspection | S. Dlamini | 40 | 1 | Planned | Critical | [39 empty] | █
T-015 | Year-end full facility inspection | ALL | Inspection | T. Mokoena | 50 | 2 | Planned | Critical | [49 empty] | █ | █
LEGEND — Task Type: | PM | PdM | CBM | Overhaul | Inspection | Lubrication | Calibration

## 📋 Work Orders
WORK ORDER REGISTER
► Yellow cells = manual input ¦ Blue cells = auto-calculated ¦ Status dropdown controls row colour
WO Number | Task ID | Description | Equipment | Priority | Status | Assigned To | Planned Date | Completion Date | Est. Hours | Actual Hours | Est. Cost (R)
WO-2025-001 | T-001 | 30,000hr PM — Feed Pump P-101 | P-101 | High | Planned | T. Mokoena |  |  | 8 | 0 | 3500
WO-2025-002 | T-002 | Gearbox oil change GB-001 | GB-001 | Medium | Planned | S. Dlamini |  |  | 4 | 0 | 800
WO-2025-003 | T-003 | Conveyor belt inspection CV-001 | CV-001 | High | Planned | R. Botha |  |  | 6 | 0 | 1200
WO-2025-004 | T-004 | Vibration analysis M-101 | M-101 | High | Planned | K. Sithole |  |  | 3 | 0 | 500
WO-2025-005 | T-005 | Crusher overhaul | M-101 | Critical | Planned | T. Mokoena |  |  | 80 | 0 | 45000
WO-2025-006 | T-006 | Lubrication round — all pumps | P-101 | Low | Planned | J. van Wyk |  |  | 4 | 0 | 300
WO-2025-007 | T-007 | Ball mill liner replacement | M-102 | Critical | Planned | A. Mahlangu |  |  | 60 | 0 | 38000
WO-2025-008 | T-008 | Cooling fan bearing replacement | FN-001 | Medium | Planned | R. Botha |  |  | 8 | 0 | 2200
WO-2025-009 | T-009 | Compressor valve overhaul | C-101 | High | Planned | S. Dlamini |  |  | 16 | 0 | 9500
WO-2025-010 | T-010 | Tailings pump impeller check | P-102 | Medium | Planned | K. Sithole |  |  | 6 | 0 | 1800
TOTALS | [8 empty] | 195 | 0 | 102800

## 👥 Resources
RESOURCE ALLOCATION — Hours per Technician per Month
Technician | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | TOTAL
T. Mokoena | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Available hrs | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 2112
S. Dlamini | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Available hrs | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 2112
R. Botha | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Available hrs | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 2112
K. Sithole | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Available hrs | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 2112
J. van Wyk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Available hrs | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 2112
A. Mahlangu | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Available hrs | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 2112

## 📊 KPIs
KPI SUMMARY — Auto-calculated from Work Order Register
PM COMPLIANCE | % of planned WOs completed on time | 0% | Target: ≥ 85%
SCHEDULE ADHERENCE | WOs completed vs total WOs raised | 0% | Target: ≥ 90%
TOTAL WORK ORDERS | All WOs in the register | 10
OPEN WORK ORDERS | WOs with status = Planned or In Progress | 10
OVERDUE WORK ORDERS | WOs with status = Overdue | 0 | Target: 0
BACKLOG HOURS | Est. hours on open + overdue WOs | 195
TOTAL EST. COST | Sum of all estimated costs (R) | 102800
CRITICAL WOs OPEN | Priority = Critical AND status ≠ Complete | 2 | Target: 0