## ℹ Instructions
MAINTENANCE PLANNING TOOL — USER GUIDE
OVERVIEW
This workbook contains 5 sheets: Instructions, Annual Planner (Gantt), Work Order Register, Resource Allocation, and KPI Summary. All sheets link together automatically.
STEP 1 — Settings
Go to the 'Settings' tab. Enter your facility name, planning year, total planned hours per month, and the list of technicians. These feed into the Resource sheet.
STEP 2 — Annual Planner
Go to '📅 Annual Planner'. Add each maintenance task: enter the Task ID, description, equipment tag, type (PM/PdM/CBM/Overhaul), responsible person, planned start week, and duration in weeks. The Gantt bars fill automatically.
STEP 3 — Work Orders
Go to '📋 Work Orders'. Log each work order as it is raised: WO number, linked task, equipment, priority, status, estimated and actual hours, and cost. Status dropdown controls the row colour (Planned / In Progress / Complete / Overdue / Cancelled).
STEP 4 — Resource Allocation
Go to '👥 Resources'. This sheet shows planned hours per technician per month, compared to their available hours. Over-allocated months are highlighted in red automatically.
STEP 5 — KPI Summary
Go to '📊 KPIs'. All metrics (PM Compliance, Schedule Adherence, Backlog, Cost Variance) calculate automatically from the Work Order sheet. No manual entry needed.
COLOUR CODING
Yellow cells = manual input required. Blue cells = auto-calculated (do not edit). Green rows = Complete. Red rows = Overdue. Orange rows = In Progress. Gantt bars: dark fill = planned window, green fill = complete.
CONTACT
Template by Katleho Khoarane ¦ Mechanical Engineer ¦ MEng Candidate — CUT ¦ Turbomachinery · Mining · Energy ¦ linkedin.com/in/katleho-khoarane

## ⚙ Settings
SETTINGS — Edit yellow cells only
Facility Name | Acme Mining — Plant A
Planning Year | 2025
Total weeks in year | 52
Std hours/day | 8
Std working days/month | 22
TECHNICIANS (one per row below)
T. Mokoena
S. Dlamini
R. Botha
K. Sithole
J. van Wyk
A. Mahlangu
NAMED_TECH_START

## 📅 Annual Planner
ANNUAL MAINTENANCE PLANNER — GANTT VIEW
[9 empty] | JAN |  |  |  | FEB |  |  |  | MAR |  |  |  |  | APR |  |  |  | MAY |  |  |  | JUN |  |  |  | JUL |  |  |  |  | AUG |  |  |  | SEP |  |  |  | OCT |  |  |  |  | NOV |  |  |  | DEC
Task ID | Description | Equipment | Type | Responsible | Start Week | Duration (wks) | Status | Priority | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
T-001 | 30,000hr PM — Feed Pump P-101 | P-101 | PM | T. Mokoena | 1 | 1 | Planned | High | █
T-002 | Gearbox oil change — GB-001 | GB-001 | PM | S. Dlamini | 2 | 1 | Planned | Medium |  | █
T-003 | Conveyor belt inspection — CV-001 | CV-001 | Inspection | R. Botha | 3 | 1 | Planned | High |  |  | █
T-004 | Vibration analysis — M-101 | M-101 | PdM | K. Sithole | 4 | 1 | Planned | High |  |  |  | █
T-005 | Crusher overhaul | M-101 | Overhaul | T. Mokoena | 5 | 4 | Planned | Critical |  |  |  |  | █ | █ | █ | █
T-006 | Lubrication round — all pumps | P-101 | Lubrication | J. van Wyk | 1 | 1 | Planned | Low | █
T-007 | Ball mill liner replacement | M-102 | Overhaul | A. Mahlangu | 12 | 3 | Planned | Critical | [11 empty] | █ | █ | █
T-008 | Cooling fan bearing replacement | FN-001 | PM | R. Botha | 8 | 1 | Planned | Medium | [7 empty] | █
T-009 | Compressor valve overhaul | C-101 | Overhaul | S. Dlamini | 16 | 2 | Planned | High | [15 empty] | █ | █
T-010 | Tailings pump impeller check | P-102 | Inspection | K. Sithole | 20 | 1 | Planned | Medium | [19 empty] | █
T-011 | Conveyor CV-002 belt tension | CV-002 | PM | J. van Wyk | 24 | 1 | Planned | Low | [23 empty] | █
T-012 | Gearbox GB-002 oil analysis | GB-002 | PdM | T. Mokoena | 26 | 1 | Planned | Medium | [25 empty] | █
T-013 | Motor alignment check — M-101 | M-101 | Inspection | A. Mahlangu | 30 | 1 | Planned | High | [29 empty] | █
T-014 | Annual safety valve test | C-101 | Inspection | S. Dlamini | 40 | 1 | Planned | Critical | [39 empty] | █
T-015 | Year-end full facility inspection | ALL | Inspection | T. Mokoena | 50 | 2 | Planned | Critical | [49 empty] | █ | █
LEGEND — Task Type: | PM | PdM | CBM | Overhaul | Inspection | Lubrication | Calibration

## 📋 Work Orders
WORK ORDER REGISTER
► Yellow cells = manual input ¦ Blue cells = auto-calculated ¦ Status dropdown controls row colour
WO Number | Task ID | Description | Equipment | Priority | Status | Assigned To | Planned Date | Completion Date | Est. Hours | Actual Hours | Est. Cost (R)
WO-2025-001 | T-001 | 30,000hr PM — Feed Pump P-101 | P-101 | High | Planned | T. Mokoena |  |  | 8 | 0 | 3500
WO-2025-002 | T-002 | Gearbox oil change GB-001 | GB-001 | Medium | Planned | S. Dlamini |  |  | 4 | 0 | 800
WO-2025-003 | T-003 | Conveyor belt inspection CV-001 | CV-001 | High | Planned | R. Botha |  |  | 6 | 0 | 1200
WO-2025-004 | T-004 | Vibration analysis M-101 | M-101 | High | Planned | K. Sithole |  |  | 3 | 0 | 500
WO-2025-005 | T-005 | Crusher overhaul | M-101 | Critical | Planned | T. Mokoena |  |  | 80 | 0 | 45000
WO-2025-006 | T-006 | Lubrication round — all pumps | P-101 | Low | Planned | J. van Wyk |  |  | 4 | 0 | 300
WO-2025-007 | T-007 | Ball mill liner replacement | M-102 | Critical | Planned | A. Mahlangu |  |  | 60 | 0 | 38000
WO-2025-008 | T-008 | Cooling fan bearing replacement | FN-001 | Medium | Planned | R. Botha |  |  | 8 | 0 | 2200
WO-2025-009 | T-009 | Compressor valve overhaul | C-101 | High | Planned | S. Dlamini |  |  | 16 | 0 | 9500
WO-2025-010 | T-010 | Tailings pump impeller check | P-102 | Medium | Planned | K. Sithole |  |  | 6 | 0 | 1800
TOTALS | [8 empty] | 195 | 0 | 102800

## 👥 Resources
RESOURCE ALLOCATION — Hours per Technician per Month
Technician | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | TOTAL
T. Mokoena | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Available hrs | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 2112
S. Dlamini | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Available hrs | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 2112
R. Botha | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Available hrs | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 2112
K. Sithole | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Available hrs | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 2112
J. van Wyk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Available hrs | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 2112
A. Mahlangu | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Available hrs | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 176 | 2112

## 📊 KPIs
KPI SUMMARY — Auto-calculated from Work Order Register
PM COMPLIANCE | % of planned WOs completed on time | 0% | Target: ≥ 85%
SCHEDULE ADHERENCE | WOs completed vs total WOs raised | 0% | Target: ≥ 90%
TOTAL WORK ORDERS | All WOs in the register | 10
OPEN WORK ORDERS | WOs with status = Planned or In Progress | 10
OVERDUE WORK ORDERS | WOs with status = Overdue | 0 | Target: 0
BACKLOG HOURS | Est. hours on open + overdue WOs | 195
TOTAL EST. COST | Sum of all estimated costs (R) | 102800
CRITICAL WOs OPEN | Priority = Critical AND status ≠ Complete | 2 | Target: 0

## Premium Guide
Maintenance Planning Excel — PREMIUM UPGRADE GUIDE
Original template preserved. Added premium sheets turn the file into a semi-automated maintenance management tool.
Step | What to do | Outcome
1 | Enter field data | Complete the original inspection/report sheet. Yellow cells and result columns are input fields.
2 | Use dropdowns | Use standardised results, priority, status, criticality and RCA decision fields to keep data clean.
3 | Review dashboard | Open the dashboard/summary sheet to view compliance, open actions, overdue actions and management risk indicators.
4 | Close actions | Transfer defects/recommendations to the Action Tracker with owner, due date, status and verification evidence.
5 | Issue report | Use the original form for site records and the added registers for meetings, audits and maintenance planning.
Upgrades Implemented
• PM frequency engine added to generate next due dates from daily/weekly/monthly/quarterly/annual frequencies.
• Backlog ageing matrix added for open work by 0–7, 8–30, 31–60 and 60+ days.
• Shutdown planner added for tasks, dependencies, permits, spares, resources and readiness.
• Cost variance tracker added for budget vs actual cost control.
• Premium executive dashboard added for PM compliance, schedule compliance, backlog and action status.

## Lists
CONTROL LISTS / DROPDOWNS
Edit these lists if your site uses different status, priority, failure mode or criticality labels.
Status | Priority | Result | Severity | Failure Mode | Criticality | Shift | RCA Required
Open | Critical | ✓ | 1 | Mechanical | A - Critical | Day | Yes
In Progress | High | ✗ | 2 | Electrical | B - Important | Night | No
Complete | Medium | N/A | 3 | Lubrication | C - General | A | TBC
Overdue | Low | Monitor | 4 | Hydraulic |  | B
Deferred | Monitor |  | 5 | Pneumatic |  | C
Cancelled |  |  |  | Instrumentation |  | D
Verified |  |  |  | Process
Operator
Design
Unknown

## Action Tracker
ACTION TRACKER
Central register for defects, recommendations, close-out dates, and verification.
Source/Sheet | Asset / Equipment | Finding / Defect | Risk / Impact | Priority | Responsible Person | Due Date | Status | Close-out Date | Verification / Evidence | Days Overdue
[7 empty] | Open |  |  | 0
[7 empty] | Open |  |  | 0
[7 empty] | Open |  |  | 0
[7 empty] | Open |  |  | 0
[7 empty] | Open |  |  | 0
[7 empty] | Open |  |  | 0
[7 empty] | Open |  |  | 0
[7 empty] | Open |  |  | 0
[7 empty] | Open |  |  | 0
[7 empty] | Open |  |  | 0
[7 empty] | Open |  |  | 0
[7 empty] | Open |  |  | 0
[7 empty] | Open |  |  | 0
[7 empty] | Open |  |  | 0
[7 empty] | Open |  |  | 0
[7 empty] | Open |  |  | 0
[7 empty] | Open |  |  | 0
[7 empty] | Open |  |  | 0
[7 empty] | Open |  |  | 0
[7 empty] | Open |  |  | 0
[7 empty] | Open |  |  | 0
[7 empty] | Open |  |  | 0
[7 empty] | Open |  |  | 0
[7 empty] | Open |  |  | 0
[7 empty] | Open |  |  | 0
[7 empty] | Open |  |  | 0
[7 empty] | Open |  |  | 0
[7 empty] | Open |  |  | 0
[7 empty] | Open |  |  | 0
[7 empty] | Open |  |  | 0
Formulas:
Days Overdue = IF(AND([Due Date]<>"",[Status]<>"Complete",[Status]<>"Verified"),MAX(0,TODAY()-[Due Date]),0)

## PM Frequency Engine
PM FREQUENCY ENGINE
Build a master PM register and calculate next due dates automatically.
PM ID | Equipment Tag | Task Description | Frequency | Last Done | Next Due | Criticality | Responsible | WO Template | Status | Action Required | Notes | Running Hours Basis
PM-001 |  |  | M | [5 empty] | Open
PM-002 | [8 empty] | Open
PM-003 | [8 empty] | Open
PM-004 | [8 empty] | Open
PM-005 | [8 empty] | Open
PM-006 | [8 empty] | Open
PM-007 | [8 empty] | Open
PM-008 | [8 empty] | Open
PM-009 | [8 empty] | Open
PM-010 | [8 empty] | Open
PM-011 | [8 empty] | Open
PM-012 | [8 empty] | Open
PM-013 | [8 empty] | Open
PM-014 | [8 empty] | Open
PM-015 | [8 empty] | Open
PM-016 | [8 empty] | Open
PM-017 | [8 empty] | Open
PM-018 | [8 empty] | Open
PM-019 | [8 empty] | Open
PM-020 | [8 empty] | Open
PM-021 | [8 empty] | Open
PM-022 | [8 empty] | Open
PM-023 | [8 empty] | Open
PM-024 | [8 empty] | Open
PM-025 | [8 empty] | Open
PM-026 | [8 empty] | Open
PM-027 | [8 empty] | Open
PM-028 | [8 empty] | Open
PM-029 | [8 empty] | Open
PM-030 | [8 empty] | Open

## Backlog Aging
BACKLOG AGEING MATRIX
Track open work orders by age band and priority.
WO Number | Equipment Tag | Description | Priority | Date Raised | Age (days) | Age Band | Status | Responsible | Action
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Formulas:
Age (days) = IF([Date Raised]="","",TODAY()-[Date Raised])

## Shutdown Planner
SHUTDOWN PLANNING MODULE
Plan task sequence, dependencies, permits, spares, resources and readiness.
Shutdown ID | Task ID | Task Description | Equipment | Predecessor | Start | Finish | Duration hrs | Permit Required? | Spares Ready? | Resources Ready? | Risk | Status | Comments
SD-001 | [7 empty] | No | No | No | Medium | Planned
SD-001 | [7 empty] | No | No | No | Medium | Planned
SD-001 | [7 empty] | No | No | No | Medium | Planned
SD-001 | [7 empty] | No | No | No | Medium | Planned
SD-001 | [7 empty] | No | No | No | Medium | Planned
SD-001 | [7 empty] | No | No | No | Medium | Planned
SD-001 | [7 empty] | No | No | No | Medium | Planned
SD-001 | [7 empty] | No | No | No | Medium | Planned
SD-001 | [7 empty] | No | No | No | Medium | Planned
SD-001 | [7 empty] | No | No | No | Medium | Planned
SD-001 | [7 empty] | No | No | No | Medium | Planned
SD-001 | [7 empty] | No | No | No | Medium | Planned
SD-001 | [7 empty] | No | No | No | Medium | Planned
SD-001 | [7 empty] | No | No | No | Medium | Planned
SD-001 | [7 empty] | No | No | No | Medium | Planned
SD-001 | [7 empty] | No | No | No | Medium | Planned
SD-001 | [7 empty] | No | No | No | Medium | Planned
SD-001 | [7 empty] | No | No | No | Medium | Planned
SD-001 | [7 empty] | No | No | No | Medium | Planned
SD-001 | [7 empty] | No | No | No | Medium | Planned
SD-001 | [7 empty] | No | No | No | Medium | Planned
SD-001 | [7 empty] | No | No | No | Medium | Planned
SD-001 | [7 empty] | No | No | No | Medium | Planned
SD-001 | [7 empty] | No | No | No | Medium | Planned
SD-001 | [7 empty] | No | No | No | Medium | Planned

## Cost Variance
MAINTENANCE COST PLAN VS ACTUAL
Compare planned budget to actual cost by work order or task.
WO / Task | Equipment | Cost Category | Planned Cost | Actual Cost | Variance | Variance % | Reason | Owner | Corrective Action | Status
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open

## Premium Executive Dashboard
MAINTENANCE PLANNING EXECUTIVE DASHBOARD
Management summary across PM frequency, backlog, shutdown readiness and action close-out.
Metric | Value | Interpretation
PM tasks registered | 30 | Rows in PM master register
PM overdue | 0 | Next due dates before today
Backlog open | 3 | Work not complete
Backlog 60+ days | 0 | High ageing risk
Shutdown tasks not ready | 25 | Readiness attention
Cost overrun total | 0 | Actual cost above plan
Open actions | 3 | Action tracker not closed
Overall status | PM OVERDUE | Management interpretation